## Manual Test Cases
ID | Module | Test case | Preconditions | Steps | Expected result | Actual result | Status | Tester | Date | Also automated by
TC-01 | Auth | Role selection leads to login | Logged out | 1. Open /role-select 2. Click "Debater" | Login page opens showing "Signing in as DEBATER" |  |  |  |  | Vitest, Playwright
TC-02 | Auth | Sign up as Debater | Logged out | 1. Open /signup 2. Fill name, username, e-mail, password x2 3. Click Create Account | Account created; Debater dashboard opens |  |  |  |  | Playwright
TC-03 | Auth | Sign up as Judge shows expertise fields | Role JUDGE selected | 1. Open /signup 2. Choose Judge | Expertise and Years of Experience fields appear |  |  |  |  | Vitest
TC-04 | Auth | Password mismatch on sign-up | Logged out | 1. Enter different passwords 2. Submit | Error "Passwords do not match"; no account created |  |  |  |  | Vitest
TC-05 | Auth | Short password on sign-up | Logged out | 1. Enter password "abc" twice 2. Submit | Error "Password must be at least 6 characters" |  |  |  |  | Vitest
TC-06 | Auth | Duplicate username | User debater1 exists | Sign up again with username debater1 | Error "Username already taken" |  |  |  |  | JUnit, Postman
TC-07 | Auth | Login with username | Account exists | Log in with username + password | Correct dashboard opens for the role |  |  |  |  | Vitest, Playwright
TC-08 | Auth | Login with e-mail | Account exists | Log in with e-mail + password | Login succeeds |  |  |  |  | JUnit, Postman
TC-09 | Auth | Wrong password | Account exists | Log in with a wrong password | Error "Invalid credentials"; stays on login |  |  |  |  | Playwright
TC-10 | Auth | Log out | Logged in | 1. Open avatar menu 2. Log Out 3. Confirm | Session cleared; protected pages redirect to role selection |  |  |  |  | Playwright
TC-11 | Session | Second tab logs in as another user | Logged in as Debater in tab A | In tab B log in as a Judge | Tab A shows "User Account Switched" with the judge username |  |  |  |  | Vitest, Playwright
TC-12 | Session | Second tab logs out | Logged in, two tabs open | Log out in tab B | Tab A shows "Session Expired / Logged Out" |  |  |  |  | Vitest, Playwright
TC-13 | Session | Expired session | Logged in; token expired (or edited in DevTools) | Open Notifications | User is sent to the login page |  |  |  |  | Playwright (fails: DEF-05)
TC-14 | Access | Visitor opens organizer dashboard | Logged out | Open /dashboard/organizer | Redirected to role selection |  |  |  |  | Vitest, Playwright
TC-15 | Access | Debater opens Create Tournament | Logged in as Debater | Open /create-tournament | Redirected to home |  |  |  |  | Vitest, Playwright
TC-16 | Access | Judge opens debater dashboard | Logged in as Judge | Open /dashboard/debater | Redirected to home |  |  |  |  | Vitest
TC-17 | Tournament | Create tournament (6-step wizard) | Logged in as Organizer; 2 debaters and 1 judge exist | 1. Name + debate type 2. Type 3. Two schools with debaters 4. Add judge 5. Criteria 6. Review, Create | Tournament page opens; ACTIVE; 2 schools |  |  |  |  | Playwright, JUnit
TC-18 | Tournament | Wizard requires a name | Organizer on wizard step 1 | Click Next with an empty name | Error "Please enter tournament name"
TC-19 | Tournament | Same debater in two schools | Organizer on wizard | Add the same debater to two schools and create | Error "already assigned to a school" |  |  |  |  | JUnit
TC-20 | Tournament | Add same judge twice | Tournament with judge J | Add judge J again | Error "Judge already added" |  |  |  |  | JUnit, Postman
TC-21 | Match | Create a match | Tournament with 2 schools | Create Match: pick schools, topic, judges | Match appears in Round 1 as UPCOMING; judges notified |  |  |  |  | JUnit, Postman
TC-22 | Match | School cannot debate itself | Tournament exists | Create match with the same school on both sides | Error shown; match not created |  |  |  |  | JUnit, Postman
TC-23 | Scoring | Judge sees custom criteria | Organizer defined custom criteria | Judge opens score sheet | Organizer's criteria are the column headers |  |  |  |  | Playwright (fails: DEF-03)
TC-24 | Scoring | Judge submits score sheet | Judge assigned to match | Enter scores and Submit | Success message; organizer notified |  |  |  |  | Playwright, Postman
TC-25 | Scoring | Reopen after submitting | Judge already submitted | Open the score sheet again | "Score Sheet Submitted" message shown |  |  |  |  | Playwright (fails: DEF-04)
TC-26 | Scoring | Match result after all judges submit | Two judges assigned | Both judges submit | Match COMPLETED; winner by average; best speaker by votes |  |  |  |  | JUnit, Postman
TC-27 | Scoring | Leaderboard & stats | Completed match | Open Leaderboard tab and debater profiles | Winner +2 points; wins/losses updated |  |  |  |  | JUnit, Postman
TC-28 | Social | Send connection request | Two debaters | A clicks Connect on B's profile | B sees a pending request |  |  |  |  | JUnit, Postman
TC-29 | Social | Accept connection | Pending request | B accepts | Both see each other in connections |  |  |  |  | JUnit, Postman
TC-30 | Social | Block user | A and B connected | A blocks B | Connection removed; B cannot send requests |  |  |  |  | JUnit
TC-31 | Social | Send message | Two users | A sends a message to B | B sees the message |  |  |  |  | JUnit, Postman
TC-32 | Social | Diary post, like, comment | Logged in | Write post; another user likes and comments | Counts update; comment visible |  |  |  |  | JUnit, Postman
TC-33 | Social | Organizer verifies diary post | Diary post exists | Debater tries to verify, then organizer verifies | Debater blocked; organizer succeeds |  |  |  |  | JUnit, Postman
TC-34 | Social | Calendar event | Logged in | Create an event | Event listed in calendar |  |  |  |  | JUnit, Postman
TC-35 | Notifications | Unread count and mark read | Has notifications | Open bell; open a notification | Count decreases |  |  |  |  | Postman
TC-36 | Public | Home page for visitors | Logged out | Open / | Tournaments, top debaters and live matches load |  |  |  |  | Playwright (fails: DEF-11)
TC-37 | Public | Search | Data exists | Search for a debater or tournament name | Matching results shown |  |  |  |  | Playwright, Postman
TC-38 | Public | Newsletter subscribe | Logged out | Enter e-mail in footer and subscribe | Success message; invalid e-mail rejected |  |  |  |  | JUnit, Postman
TC-39 | Security | Edit another user's profile | Two accounts | Send PUT /api/users/{otherId} with your token | Request refused (403) |  |  |  |  | JUnit, Postman (fails: DEF-01)
TC-40 | UI | Mobile layout | Phone or 375 px window | Open home page | No horizontal scrolling; menu usable |  |  |  |  | Playwright

## Defect Log
ID | Severity | Area | Title | Details | Found by | Suggested fix | Status | Assigned to | Fixed in commit
DEF-01 | High | Security | Any logged-in user can edit another user's profile | PUT /api/users/{id} updates whichever id is in the URL; there is no check that it belongs to the caller. Debater A changed Debater B's bio (the profile-picture upload endpoint follows the same pattern). | JUnit OwnershipSecurity · Postman 06 | Compare the id with the authenticated user (or allow organizers only) before updating. | Open
DEF-02 | High | Security | Discussion comments can be posted under someone else's name | POST /api/discussion takes the author from the "userId" field in the request body instead of the login token. | JUnit OwnershipSecurity · Postman 06 | Ignore userId in the body; use the authenticated user. | Open
DEF-03 | High | Functional | Judge's score sheet ignores the organizer's custom criteria | GET /api/score-templates/{id} fails with "Type definition error ... ByteBuddyInterceptor" (a raw JPA entity with a lazy proxy is returned). The page swallows the error and silently falls back to built-in criteria. | JUnit Workflow · Postman 04 · Playwright 05 | Return a DTO (id, name, criteriaJson) instead of the entity. | Open
DEF-04 | Medium | Functional | "Already submitted" check on the score sheet never works | GET /api/score-sheets/{match}/{judge} fails with the same serialization error, so a judge who already submitted sees an empty form again; re-submitting is then rejected by the server. | JUnit Workflow · Postman 04 · Playwright 05 | Return a DTO for ScoreSheetSubmission. | Open
DEF-05 | Medium | Security / UX | Expired or invalid login returns 403 instead of 401, so users are never logged out | Spring Security has no authentication entry point configured, so missing/expired tokens get 403. The frontend only logs out on 401, so an expired session leaves the user on a page where every request fails. | JUnit RBAC · Postman 03 · Playwright 02 | Add .exceptionHandling(e -> e.authenticationEntryPoint(new HttpStatusEntryPoint(HttpStatus.UNAUTHORIZED))). | Open
DEF-06 | Medium | Security | An organizer can delete another organizer's tournament | DELETE /api/tournaments/{id} checks the ORGANIZER role but not ownership. | JUnit OwnershipSecurity | Allow delete only when tournament.organizer is the caller. | Open
DEF-07 | Medium | Security | Any logged-in user can delete anyone's discussion comment | DELETE /api/discussion/{id} has no ownership check. | JUnit OwnershipSecurity · Postman 06 | Allow only the author (or the tournament organizer). | Open
DEF-08 | Medium | Privacy | Public user list exposes every e-mail address | GET /api/users is public and returns each user's e-mail to anonymous visitors. | JUnit OwnershipSecurity · Postman 06 | Use a public profile DTO without e-mail, or require login. | Open
DEF-09 | Low | Security | Users can mark other users' notifications as read | PUT /api/notifications/{id}/read receives the username but never checks it. | JUnit OwnershipSecurity · Postman 06 | Check notification.user == caller. | Open
DEF-10 | Low | API | Role-denied requests return 400 instead of 403 | GlobalExceptionHandler catches RuntimeException, which includes Spring's AccessDeniedException, and turns "Access Denied" into 400. Access is still correctly blocked. | JUnit RBAC · Postman 03/04 | Add an @ExceptionHandler(AccessDeniedException.class) returning 403. | Open
DEF-11 | Low | Functional | Home page always shows 0 live matches to visitors | The public home page calls GET /api/matches/live, which is not in the public list in SecurityConfig, so visitors get 403 (also logged as a console error by Lighthouse). | JUnit RBAC · Postman 01 · Playwright 04 · Lighthouse | Permit GET /api/matches/** for everyone. | Open
DEF-12 | Low | API | /api/auth/me without a token returns 400 (server error) instead of 401 | /api/auth/** is fully public, so the controller runs with no Authentication and throws a NullPointerException. | JUnit RBAC · Postman 02 | Permit only /api/auth/login and /signup; require auth for /me. | Open
DEF-13 | Low | Validation | Sign-up accepts invalid e-mail addresses | SignupRequest has no validation annotations, so "not-an-email" is stored. | JUnit Auth · Postman 02 | Add @Valid with @Email/@NotBlank/@Size on SignupRequest. | Open
DEF-14 | Low | UI | Session warning modal text is hard to read | SessionChangedModal still uses the old dark-theme classes (glass-dark, text-white), so after the UI refresh the title and message are white on a light panel. | Playwright screenshot review | Restyle the modal with the new theme colors. | Open
DEF-15 | Low | Accessibility | Login page accessibility issues | The show/hide password button has no accessible name; some text fails color-contrast; pages have no <main> landmark or meta description. | Lighthouse | Add aria-label to icon buttons, a <main> element and a meta description. | Open

## Automated Results
Level | Tool | Tests | Passed | Failed | Coverage (lines) | Report file
Backend unit tests | JUnit 5 + Mockito | 46 | 46 | 0 | 86.9% (all backend) | reports/backend/jacoco/index.html
Backend integration + RBAC | MockMvc + H2 | 70 | 55 | 15 |  | reports/backend/surefire-reports/
Frontend component tests | Vitest + RTL | 52 | 52 | 0 | 78.9% | reports/frontend/coverage/index.html
API end-to-end (assertions) | Postman / Newman | 197 | 181 | 16 |  | reports/newman/api-report.html
Browser end-to-end | Playwright (Edge) | 25 | 21 | 4 |  | reports/playwright/html/index.html